## Timeline
Workstream | Start_Date | End_Date | Duration_Weeks | Is_Milestone | MILESTONES
Planning | 2025-01-01 | 2025-03-31 | 13 | FALSE | Milestone_Name | Target_Date | Description
Appraisals | 2025-01-15 | 2025-06-30 | 24 | FALSE | Board Approval | 2025-03-15 | Internal approval
Due Diligence | 2025-04-01 | 2025-09-30 | 26 | FALSE | Prospectus Filed | 2025-10-15 | Regulatory filing
Structuring | 2025-06-01 | 2025-09-30 | 17 | FALSE | IPO Launch | 2025-12-01 | Market debut
Prospectus | 2025-08-01 | 2025-11-30 | 17 | FALSE
Marketing | 2025-10-01 | 2025-11-30 | 9 | FALSE
Filing | 2025-10-15 | 2025-11-15 | 4 | FALSE
Launch | 2025-12-01 | 2025-12-01 | 0 | TRUE